## Manual Chart
GANTT CHART
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Phase 1 - Requirments
| SRS | 2025-02-19 | 2025-02-27 | 8 | All | 100% | bar: WEEK 1 M to WEEK 1 W; WEEK 2 M; WEEK 4 F
| Use Case Specification Documentation | 2025-02-19 | 2025-02-28 | 9 | All | 100% | bar: WEEK 1 W; WEEK 2 M to WEEK 2 T; WEEK 4 F
| UML Case Diagram | 2025-02-19 | 2025-03-01 | 12 | All | 100% | bar: WEEK 1 W to WEEK 2 M; WEEK 4 F
| Class Diagram | 2025-02-19 | 2025-03-01 | 12 | All | 100% | bar: WEEK 1 Th to WEEK 2 M; WEEK 4 F
| Sequence Diagram | 2025-02-19 | 2025-03-01 | 12 | All | 100% | bar: WEEK 1 F to WEEK 2 M; WEEK 4 F
All | bar: WEEK 2 M; WEEK 4 F
Phase 2 - Design
| Design Software Document | 2025-03-05 | 2025-04-09 | 34 | Raymond | 100% | bar: WEEK 2 M; WEEK 3 M; WEEK 3 F; WEEK 4 W; WEEK 4 F to WEEK 5 T
| classes Finalization | 2025-03-05 | 2025-04-09 | 34 | Vish | 100% | bar: WEEK 2 M; WEEK 3 M; WEEK 3 F; WEEK 4 W; WEEK 4 F to WEEK 5 T
| Use Case / Sequence Diagrams Finalization | 2025-03-05 | 2025-04-09 | 34 | Raymond | 100% | bar: WEEK 2 M; WEEK 3 M; WEEK 3 F; WEEK 4 W; WEEK 4 F
| Presentation | 2025-03-05 | 2025-04-09 | 34 | Kurt | 100% | bar: WEEK 2 M; WEEK 3 M; WEEK 4 F to WEEK 5 T
Phase 3 - Implementation
| Implement their set of classes | 2025-04-09 | 2025-05-07 | 28 | Kurt | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 6 M to WEEK 6 Th; WEEK 7 T; WEEK 7 Th; WEEK 8 T to WEEK 8 Th
| Implement their set of classes | 2025-04-09 | 2025-05-07 | 28 | Vish | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 7 T; WEEK 7 Th; WEEK 8 T to WEEK 8 Th
| Implement their set of classes | 2025-04-09 | 2025-05-07 | 28 | Raymond | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 7 T; WEEK 7 Th; WEEK 8 T to WEEK 8 Th
| Touch Base and check each others work | 2025-04-09 | 2025-05-07 | 28 | All | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 9 M to WEEK 9 Th
| Make sure it works with each others | 2025-04-09 | 2025-05-07 | 28 | All | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 9 F to WEEK 10 Th
| Final fixes and changes/ Fufilling Reqs. | 2025-04-09 | 2025-05-07 | 28 | Raymond | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 11 M to WEEK 11 F
Phase 4 - Testing & Maintenance
| Creating a Testing Doc / Project Scedule | 2025-04-09 | 2025-05-07 | 28 | All | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 12 M
| Make Tests for their classes | 2025-04-09 | 2025-05-07 | 28 | All | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 12 T
| Check for Error Handeling | 2025-04-09 | 2025-05-07 | 28 | Raymond | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 12 W to WEEK 12 F
| Check for any loose ends or flaws | 2025-04-09 | 2025-05-07 | 28 | All | 100% | bar: WEEK 2 M; WEEK 4 F; WEEK 12 W to WEEK 12 F