## Manual Chart
GANTT CHART
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Phase 1 - Requirments
| SRS | 2025-02-19 | 2025-02-27 | 8 | All | 100% | bar: WEEK 1 M to WEEK 1 W
| Use Case Specification Documentation | 2025-02-19 | 2025-02-28 | 9 | All | 100% | bar: WEEK 1 W; WEEK 2 M to WEEK 2 T
| UML Case Diagram | 2025-02-19 | 2025-03-01 | 12 | All | 100% | bar: WEEK 1 W to WEEK 1 F
| Class Diagram | 2025-02-19 | 2025-03-01 | 12 | All | 100% | bar: WEEK 1 Th to WEEK 1 F
| Sequence Diagram | 2025-02-19 | 2025-03-01 | 12 | All | 100% | bar: WEEK 1 F
All
Phase 2 - Design
| TBA | 2025-03-05 | 2025-04-09 | 34 | Kurt | 0%
| TBA | 2025-03-05 | 2025-04-09 | 34 | Vish | 0%
| TBA | 2025-03-05 | 2025-04-09 | 34 | Raymond | 0%
| TBA | 2025-03-05 | 2025-04-09 | 34 | All | 0%
Phase 3 - Implementation
| TBA | 2025-04-09 | 2025-05-07 | 28 | Kurt | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Vish | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Raymond | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | All | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Kurt | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Vish | 0%
Phase 3 - Testing & Maintenance
| TBA | 2025-04-09 | 2025-05-07 | 28 | All | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Kurt | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Vish | 0%
| TBA | 2025-04-09 | 2025-05-07 | 28 | Raymond | 0%